# Kirklees Service Finder

Revised option appraisal for a trusted, private and sustainable digital service

Draft for discussion  |  24 September 2026

This appraisal reframes the technical options around the intended service: helping residents and frontline staff find relevant, reliable local support while protecting people’s privacy and keeping information current. It recommends a time-limited discovery and prototype phase before selecting a production platform.

# Executive summary

The current evidence does not establish that a fully self-hosted system is the lowest-cost, most private, or most sustainable route. Local hosting may be viable, but its performance, operating requirements, privacy controls and whole-life cost have not yet been demonstrated. Cloud and supplier options also need a like-for-like assessment against the same service requirements.

The proposed decision is to approve discovery and a limited prototype, not a production build. The work should establish user needs, validate the service-data approach, define privacy and accessibility requirements, test a representative prototype, and compare three delivery models using transparent cost and demand assumptions. A production recommendation should return for approval with evidence and named operational owners.

| Decision requested | Reason |
| --- | --- |
| Approve discovery and a limited prototype. | Resolve material uncertainties before committing to a platform or ongoing operating costs. |
| Agree minimum service requirements and pass criteria. | Ensure privacy, quality, accessibility and reliability are treated as essential requirements. |
| Nominate content, service and technical owners. | The service depends on continuing partner input as well as technology. |

# 1. Purpose and scope

The Service Finder is intended to help frontline staff, partner organisations and local people find relevant support. The elevator pitch describes a service that begins with work and health, uses trusted local information, tailors results to a person’s circumstances, protects personal details, and expands over time.

This appraisal compares delivery approaches for that service. It does not assume that web scraping, generative AI, or a particular hosting model is necessary. Discovery should confirm which functions provide enough value to justify their cost and risk.

# 2. Outcomes and minimum requirements

| Outcome | Requirement to assess | Evidence / pass condition to define |
| --- | --- | --- |
| Relevant support | Results reflect agreed location, eligibility and service details; users can understand why an item is suggested. | Representative user scenarios show useful results; criteria and acceptable result quality agreed before testing. |
| Trusted, current information | Every record has a source, owner and last-checked date, with a correction and review process. | Sample audit establishes baseline accuracy and a feasible update service level. |
| Privacy in practice | Specify data processed, logs, analytics, retention, access, third parties and deletion. | Documented data flows and privacy assessment; approved retention and logging settings verified in prototype. |
| Accessible service | Support accessible, mobile-friendly use, plain language and users with varied digital confidence. | Accessibility requirements agreed and tested with intended users; findings have owners and resolution dates. |
| Reliable operation | Define availability, response time, support, recovery and incident handling. | Service levels, support arrangements and recovery objectives approved and tested. |
| Sustainable expansion | Support additional topics without losing quality or clear ownership. | Governance and content model tested against at least one potential expansion area. |
| Free at point of use | Fund the full operating model, not only initial build or licence. | Whole-life cost model includes staff, technical operations and refresh / exit costs. |

Any option that fails an agreed mandatory requirement for privacy, security, accessibility or service quality should be excluded or redesigned before weighted scoring.

# 3. Options considered

## Option 1: Partnership-hosted service

The partnership operates the application, directory and search components on infrastructure it controls. This may offer direct control over configuration and data flows. It also requires clear ownership and ongoing capacity for security updates, monitoring, backups, incident response and technical support. Local language-model inference must be tested for answer quality, speed and peak demand on realistic hardware. “Self-hosted” should not be treated as proof that data is never stored or that the service is compliant.

## Option 2: Cloud-hosted service with managed components

The application and data services run in a cloud environment, potentially using managed search or AI components. This may reduce infrastructure management and support scaling, but requires explicit controls for data location, provider access, logging, retention and sub-processors. Costs should be modelled at low, expected and high usage, including safeguards against unexpected spend and a route to export data or change providers.

## Option 3: Managed supplier or white-label product

A supplier provides a directory or service-finder platform. This may reduce the initial build and some technical support burden, but the partnership must test whether the product can meet its data, privacy, accessibility, integration and content-governance requirements. Procurement should cover service levels, data use, export, contract exit, price changes and product roadmap dependency.

## Option 4: Staged discovery and prototype

This is the recommended immediate course of action, rather than a permanent technical architecture. It tests the service model and compares representative partnership-hosted and cloud-hosted prototypes on the same data and scenarios. Include a managed supplier in the comparison if market research identifies a credible product. At the end, return with evidence to select a production option or stop / redesign.

# 4. Whole-life cost and affordability

The current appraisal’s estimates should be treated as indicative only until their assumptions and exclusions are confirmed. Prepare a common three-to-five-year cost model for each production option, showing cash costs separately from internal staff effort. Use low, expected and high demand scenarios; state the assumptions behind query volumes, response-time targets, data volumes and support coverage.

| Cost area | Include for every option |
| --- | --- |
| Initial work | Discovery, service design, user research, data preparation, procurement, implementation, integration and training. |
| People | Product/service owner, partner content owners, curation and verification, technical operations, supplier management and support. |
| Technology | Hosting, AI / search usage, licences, security tools, monitoring, backups, recovery, network and hardware replacement. |
| Assurance | Privacy, security, accessibility, legal / procurement review, user testing and independent technical review where needed. |
| Ongoing and exit | Updates, incident response, service support, growth, data export, migration, contract exit and decommissioning. |

The comparison should identify which costs are fixed, usage-dependent, one-off or recurring; what assumptions could change them; and who is expected to fund them. “Free to use” should be reported as a user-facing policy, alongside the annual funding required to sustain it.

# 5. Key risks and proposed controls

| Risk | Control to design and evidence | Proposed owner |
| --- | --- | --- |
| Sensitive details retained in prompts, logs or analytics. | Map data flows; minimise collection; set retention and deletion rules; restrict access; verify settings and backups. | Privacy lead + technical owner |
| Incorrect or stale service information. | Use approved sources; assign record owners; display source and last-checked date; define review and correction routes. | Directory/content lead + partners |
| AI output is invented, unclear or unsuitable. | Ground answers in approved records; show sources; communicate uncertainty; provide escalation routes; test difficult cases. | Product/service owner |
| Scraping is unreliable or restricted. | Review source terms and technical access; use agreed alternatives such as APIs, partner updates or manual verification. | Content lead + legal/procurement |
| Security incident or service outage. | Threat model; patching and access controls; monitoring; backups; recovery and incident exercises. | Technical owner |
| Unequal access or inaccessible interaction. | Set accessibility requirements; test with intended users; offer non-digital support routes where needed. | Product owner + accessibility lead |
| Ongoing work is not funded or owned. | Name accountable service and technical owners; cost staff time; agree partner responsibilities and capacity. | Programme sponsor |
| Supplier / platform dependency. | Require exportable data, documented interfaces, exit support, transparent pricing and transition planning. | Commercial / procurement lead |

Owners are roles to assign during discovery, not confirmed appointments. Each risk should receive a likelihood, impact, mitigation status and residual rating in the full risk register.

# 6. Evidence plan and evaluation

- Interview and test with residents, frontline staff and partner organisations to confirm priority tasks, language, accessibility and support needs.

- Audit a representative sample of local service records to establish completeness, accuracy, source availability and the effort needed to keep information current.

- Map all information flows, including prompts, search terms, logs, analytics, model providers, backups and support access; complete the appropriate privacy and security assessments.

- Compare prototype approaches using the same service data and realistic scenarios, including ambiguous searches and cases where the system should not offer a confident answer.

- Test accessibility, mobile use, response time, peak demand, recovery and content correction workflows.

- Build and independently review the whole-life cost model, demand assumptions, support model and exit costs.

Agree numeric targets before testing rather than selecting them after results are known. Measures should include verified-record coverage, recommendation usefulness, error correction time, accessibility findings resolved, response time, service availability, privacy events and cost across usage scenarios.

# 7. Governance and operating model

The service requires named accountability beyond the technology supplier or hosting team. Before production approval, agree who owns the public service, directory content, source approval, technical operations, privacy decisions, partner onboarding, complaints and incidents. Define how partners submit changes, how quickly corrections are reviewed, how unresolved disputes are handled, and how the service decides whether to add new topic areas.

# 8. Proposed recommendation and decision gates

Recommendation: approve discovery and a limited prototype, not a full production build. The current evidence is insufficient to conclude that partnership hosting is the most sustainable or lowest-cost route. It may be suitable if testing demonstrates that the partnership can meet performance, privacy, resilience and support requirements at an affordable whole-life cost.

| Gate | Required output | Decision |
| --- | --- | --- |
| 1. Discovery | Agreed requirements, user research, source audit, privacy / security scope, governance roles and demand assumptions. | Confirm whether a prototype is justified and approve the test plan. |
| 2. Prototype and comparison | Comparable prototype evidence, accessibility and quality results, cost scenarios, operating model and risk register. | Select an option, request further work, or stop / redesign. |
| 3. Production approval | Funded business case, service levels, named owners, assurance sign-off, procurement route, support and exit plan. | Approve launch, subject to agreed readiness criteria. |
| 4. Post-launch review | Usage, quality, equity, cost, privacy and content freshness measures against targets. | Continue, improve, scale or retire the service. |

# 9. Assumptions and items to confirm

- The service is intended for frontline staff, partner organisations and members of the public, and will be free at the point of use.

- The initial subject area is work and health, with possible future expansion; scope and sequencing need confirmation.

- No hosting, AI, scraping or supplier choice has been approved by this draft.

- No whole-life budget, demand forecast, service level, retention period or operating owner has been confirmed in the source material.

- All cost figures should be replaced or validated through discovery, finance review, technical assessment and, where relevant, supplier market engagement.

# Source documents

Kirklees Service Finder — Option Appraisal (Formatted), supplied PDF. Used as the source for the original options, architecture outline and indicative estimates.

Elevator Pitch, supplied DOCX. Used as the source for the intended audience, privacy promise, tailored search, service-data freshness and expansion vision.